## 17 August Report
Commission Approved Item/Project | Budget Amount | Process Complete? Y/N | Dated Comments | Encumbered? Y/N | Amount Encumbered | Contract Executed? Y/N | Invoiced? Y/N | Amount Paid YTD | Remaining Balance YTD | Dated Comments | Accrual Amount as of Report Date | Funds estimated available for reallocation (09July) | Reallocation Comments
OEMS/T Allocation at 3%
OEMS/T Allocation at 3% | 655500 | N |  | Partially | ? | 3 of 5.5 | Partially | 189383.05 | 0 | 3 of the 5.5 positions have been filled. The 2.5 positions still outstanding are: Trauma Nurse, IT Specialist, Part-time EMS Medical Director. The two regional EMS directors are Chris Threlkeld and Shirley Starling. Amount paid to date unknown. Awaiting budget numbers: April 19, 2010 (per CLC). 17 Aug: DCH Budget confirmed YTD paid out $189,383.05. | 0 | 466116.95 | No funds available. Commission voted to permit Dr. O'Neal to keep these funds to cover DPR salaries as necessary. Aug 17: DCH Budget reported $466,116.95 returned to FY 2910 general fund.
Administration and GTCNC Operations
Administrator & Bishop + Associates | 245950 | Y | Administrator added to B+A contract ($135,200 + $110,750) | Y | 245950 | Y | Y | 245950 | 0 | 5/14/2010-two payments made - $22,517 & $42,517 14 June 2010: All invoiced and paid.14June- final payments made - $44,736.43 & $25,066. Paid in Full | 0 | 0 | Anticipated all funds will be expended.
Administrative/business assistance | 50000 | Y | Carol Dixon hired thru ABACUS Temp Service start date: 09March2010. Contract end date uncertain. | unknown | ? | Y | Ongoing | 13003.19 |  | Salary Amount paid through 5/14/2010 - $5,744.05 Travel Reimbursement paid thru 5/14/2010 - $35.50 14June 2010: 5/18-Salary $955.15, July 9 update: June 22 & 25 - Travel Reimbursements from May & June - $831.08 Salary (Abacus) paid June 28 - $1910.30. Aug 17: No further information regarding this budget item will be forthcoming from DCH. | 0 | 36996.81 | Estimated: 17 weeks (06 March through 30 June) at $957.34/week plus $500.00 travel expenses = $16,774.78 Need data from DCH Budget. 17 August: Unknown- no further information is available.
Conference call account | 7200 | Y | Ongoing | Y | 7200 | NA | Ongoing | 1173.33 | 0 | 5 March 2010 - 304.760. 5/14/2010-Payments of $415.29 & $272.68 14 June 2010-Payment of $180.60. As of 09 July no new invoice accounting | 0 | 6026.67 | 17 August: Unknown- no further information is available
Website design and maintenance | 15000 | N |  | N | 0 | N | N | 0 | 0 | Not moving forward with this item in FY 2010 |  | 15000 | Will not be expended
Commission Travel/Per Diem | 10000 | N | Renee Morgan working with DCH | unknown | 0 | NA | NA | 0 | 0 | Not moving forward with this item in FY 2010 |  | 10000 | Commission will not utilize
Monthly GTCNC meeting support | 2400 | Y | Ongoing | Y | 2400 | NA | Ongoing | 609.79 | 0 | 5/14/2010-Curtis Chronister Nextel Phone - $66.42, 5/14/2010-UPS Contract delivery fees - $82.16 14June 2010: Curtis Chronister Nextel Phone 6/4-$66.42 & 6/8-$66.52, Pat O'Neal Mileage & Travel Expense 6/3-$32.94, UPS charges $4.93. July 9 - Correction: Deduct Dr. O'Neil travel from June ($-32.94) | 0 | 1790.21 | 17 August: Unknown- no further information is available. 17 August: Unknown- no further information is available
Trauma Communications Center
Staffing | 308000 | N |  | N | 0 | N | N | 0 | 0 | Not moving forward with this item in FY 2010 |  | 308000 | Will not be expended
Communications Center Lead Position | 100000 | Y | Position approved by DCH thru Temp service | N | 0 | Y | N | 0 | 0 | Ryan Goodson hired - Effective 01 July 2010 salary will be from FY 2011 |  | 100000 | Will not be expended
Consultation for GTCC | 25000 | N |  | N | 0 | N | N | 0 | 0 | Not moving forward with this item in FY 2010 |  | 25000 | Will not be expended
Call recorder | 8000 | N |  | N | 0 | N | N | 0 | 0 | Not moving forward with this item in FY 2010 |  | 8000 | Will not be expended
Hardware | 100000 | N |  | N | 0 | N | N | 0 | 0 | Not moving forward with this item in FY 2010 |  | 100000 | Will not be expended
Software | 300000 | N |  | N | 0 | N | N | 0 | 0 | Not moving forward with purchase of this item in FY 2010. GTRI to issue RFP in FY 2010 and funding in FY 2011. |  | 300000 | Will not be expended
Building Lease | 12000 | N |  | N | 0 | N | N | 0 | 0 | Not moving forward with this item in FY 2010. |  | 12000 | Will not be expended
Water/Electricity | 6000 | N |  | N | 0 | N | N | 0 | 0 | Not moving forward with this item in FY 2010 |  | 6000 | Will not be expended
Backup generator | 5000 | N |  | N | 0 | N | N | 0 | 0 | Not moving forward with this item in FY 2010 |  | 5000 | Will not be expended
Workstations | 20000 | N |  | N | 0 | N | N | 0 | 0 | Not moving forward with this item in FY 2010 |  | 20000 | Will not be expended
New Projects and System Support
Web-based Trauma Registry Support | 49550 | N | Vendor unable to meet requirements | N | 0 | N | N | 0 | 0 | Not moving forward with this item in FY 2010 |  | 49550 | Will not be expended
National Foundation for Trauma Care | 1500 | Y |  | Y | 1500 | Y | Y | 1500 | 0 | Completed |  | 0 | All will be distributed
Telemedicine (GA Partnership TeleHealth) | 200000 | Y | Direct Grant Award | Y | 200000 | Y | N | 0 | 200000 | Grant award anticipated last week of April 2010. 14 June 2010, award letter sent to GPT 09 July GPT plan approved to begin invoicing. Contract expires 30 September 2011. No invoices received or processed since last report. | 200000 | 0 | All will be distributed
National Science Foundation Center for Health Organization Transformation (CHOT) | 50000 | Y | Contract is moving through DCH legal process | Y | 50000 | Y | Y | 0 | 50000 | K# 41900-034-10100283 Moving thru DCH contracting process. Full 12-month membership for $50,000.00 14 June 2010 Contract executed and membership in effect for one year. Aug 17 - Invoice for $50,000 submitted to AP for payment 18 Aug '10. | 0 | 0 | All will be distributed
Pediatrics (Broselow Luten Solutions) | 200000 | Y | Contract is drafted and moving through DCH channels | Y | 200000 | Y | Y | 189000 | 11000 | K# PH-101002/2-00 Moving thru DCH contracting process. 14 May Dr. Ashley has signed contract. Contract sent to Dr. Broselow 14 June 2010. Dr. Ashley signed Contrated returned to DCH. 09 July:Ccontract exeacuted with Broselow and invoices received in Commission Office. Signature authorization in Process. Aug 17:Invoices paid August 2010 in amount of $189,000. | 11000 |  | All will be distributed
Trauma Center & Physician Allocation
New Trauma Center Startup Grants | 1000000 | N | Grant open for applications until 30 April | Y | 0 | N | N | 0 | 0 | DCH receiving applications. 14 May- evaluation committee met applications scored. Approval for spending to be made at 20 May Commission meeting. 14 June 2010: Commission approved spending money per evaluation subcommittee recommendations (20 May 2010) DCH in process of making awards 09 July: Funds returned back to state. This effort will be funded using FY2011 dollars | 0 | 1000000 | Returned to FY 2010 general fund on 30 June 2010
Level IV Trauma Centers | 54000 | Y |  | Y | 54000 | Y | Y | 54000 | 0 | 14 May - Not paid to date. 14 June 2010: Walton Medical Center Paid, Morgan Medical Center awaiting payment. 09 July: all Level IV centers paid | 0 | 0 | All will be distributed
Trauma Center Readiness Payments | 6696610 | Y |  | Y | 6696610 | Y | Y | 6696610 | 0 | 14 May - All centers paid in full except CHOA (x2) and Atlanta Medical. 14 June 2010 All Centers Paid except CHOA (x2) 09 July All centers paid. | 0 | 0 | All will be distributed
Performance Based Payment | 760380 | Y |  | Y | 760380 | Y | Y | 760380 | 0 | 14 May - All centers paid in full except CHOA (x2) and Atlanta Medical. 14 June 2010 All Centers Paid except CHOA (x2). 09 July All centers paid | 0 | 0 | All will be distributed
Uninsured Patient Care Payments | 6696610 | Y |  | Y | 6696610 | Y | Y | 6696610 | 0 | 14 May - All centers paid in full except CHOA (x2) and Atlanta Medical. 14 June 2010 All Centers Paid except CHOA (x2) 09 July All Centers paid 09 July Over payment the Grady of $653,204 returned back to state. | 0 | 653204 | Returned to general fund on 30 June 2010
EMS Allocation
EMS Uncompensated Care | 1000000 | N | Contract is being amended | Y | 1000000 | Y | Y | 1000000 | 0 | K# PH-10100190-99 (In process of being amended) 14 May - Amendment in DCH approval process. 14 June 2010: Amendment out to MCG for signatures 09 July: MCG amendment executed. Invoicing in process Program in process. 17 Aug: Funds not yet distributed. Aug 17: R. Medeiros confirmed $1,000,000 received and posted to this account on 16 Aug 2010. | 0 | 0 | All will be distributed
EMS Vehicle Equipment Replacement Grants | 2125000 | Y | Grant open for applications until 16 April | Y | 0 | N | N |  | 1392241.3 | Scoring subcommittee to meet at DCH building in Atlanta on Friday, 30 April. 14 May- evaluation committee met applications scored. Approval for spending to be made at 20 May Commission meeting. 14 June 2010 Commission approved evaluation subcommittee recommendation. DCH in process of making awards. 09 July: $732,758.60 (funding for 10 vehicle awards) returned back to state. Remaining $1,392,241.30 (19 vehicle awards) to be expended. The outstanding 10 EMS vehicle awards will be funding using FY2011 dollars. | 1392241.3 | 732758.6 | Returned to FY 2010 general fund on 30 June 2010
First Responder Training | 338450 | Y | Contract is drafted and moving through DCH | Y | 338448.8 | Y | Y |  | 338450 | K# 419-034-10100284-99 14 May - Dr. Ashley to sign contract 20 May. 14 June 2010 Contract executed and begin 01 July 2010, GAEMS has one full year for deliverables 09 July: No update available. Aug 17:GAEMS to submit invoice week of 23 Aug 2010. | 338450 | 0 | All will be distributed
Trauma-care Related Equipment | 338450 | Y | Contract is drafted and moving through DCH | Y | 338449.83 | Y | Y |  | 338450 | K# 419-034-10100284-99 14 May - Dr. Ashley to sign contract 20 May. 14 June 2010 Contract executed and begin 01 July 2010, GAEMS has one full year for deliverables. 09 July: No update available. Aug 17: GAEMS to submit invoices. | 338450 | 0 | All will be distributed
Unbudgeted Funds
Less: 5% Anticipated Budget Adjustment | 1150000 | [8 empty] | Not available to Commission |  | 1150000 | Will not be distributed
Operations Reserve | 469400 | [8 empty] | Not available to Commission |  | 469400 | Will not be expended.
TOTAL BUDGET | 23000000
[5 empty] | Amount Distributed YTD |  |  | 15195015.36 |  |  |  |  | Percentage of total FY 2010 Trauma Commission budget
[6 empty] | Remaining To Be Distributed in FY 2010 |  |  | 2330141.3 | Amount of FY 2010 budget to be distributed by Trauma Commission |  | 17525156.66 | 76.2%
[10 empty] | Amount of FY 2010 to be returned back to General Fund |  | 5474843.24 | 23.8%
[10 empty] | Total |  | 22999999.9 | 100%
17 August 2010 Updates

## 09 July Report
Commission Approved Item/Project | Budget Amount | Process Complete? Y/N | Dated Comments | Encumbered? Y/N | Amount Encumbered | Contract Executed? Y/N | Invoiced? Y/N | Amount Paid YTD | Remaining Balance YTD | Dated Comments | Accrual Amount as of Report Date | Funds estimated available for reallocation (09July) | Reallocation Comments
OEMS/T Allocation at 3%
OEMS/T Allocation at 3% | 655500 | N |  | Partially | ? | 3 of 5.5 | Partially | 655500 | ? | 3 of the 5.5 positions have been filled. The 2.5 positions still outstanding are: Trauma Nurse, IT Specialist, Part-time EMS Medical Director. The two regional EMS directors are Chris Threlkeld and Shirley Starling. Amount paid to date unknown. Awaiting budget numbers: April 19, 2010 (per CLC) |  | 0 | No funds available. Commission voted to permit Dr. O'Neal to keep these funds to cover DPR salaries as necessary.
Administration and GTCNC Operations
Administrator & Bishop + Associates | 245950 | Y | Administrator added to B+A contract ($135,200 + $110,750) | Y | 245950 | Y | Y | 245950 | 0 | 5/14/2010-two payments made - $22,517 & $42,517 14 June 2010: All invoiced and paid.14June- final payments made - $44,736.43 & $25,066. Paid in Full |  | 0 | Anticipated all funds will be expended.
Administrative/business assistance | 50000 | Y | Carol Dixon hired thru ABACUS Temp Service start date: 09March2010. Contract end date uncertain. | unknown | ? | Y | Ongoing | 9476.08 | 40523.92 | Salary Amount paid through 5/14/2010 - $5,744.05 Travel Reimbursement paid thru 5/14/2010 - $35.50 14June 2010: 5/18-Salary $955.15, July 9 update: June 22 & 25 - Travel Reimbursements from May & June - $831.08 Salary (Abacus) paid June 28 - $1910.30. | 7298.7 | 33225.22 | Estimated: 17 weeks (06 March through 30 June) at $957.34/week plus $500.00 travel expenses = $16,774.78 Need data from DCH Budget
Conference call account | 7200 | Y | Ongoing | Y | 7200 | NA | Ongoing | 1173.33 | 6026.67 | 5/14/2010-Payments of $415.29 & $272.68 14 June 2010-Payment of $180.60. As of 09 July no new invoice accounting | 1751.67 | 4275
Website design and maintenance | 15000 | N |  | N | 0 | N | N | 0 | 0 | Not moving forward with this item in FY 2010 |  | 15000 | Will not be expended
Commission Travel/Per Diem | 10000 | N | Renee Morgan working with DCH | unknown | 0 | NA | NA | 0 | 0 | Not moving forward with this item in FY 2010 |  | 10000 | Commission will not utilize
Monthly GTCNC meeting support | 2400 | Y | Ongoing | Y | 2400 | NA | Ongoing | 609.79 | 1790.21 | 5/14/2010-Curtis Chronister Nextel Phone - $66.42, 5/14/2010-UPS Contract delivery fees - $82.16 14June 2010: Curtis Chronister Nextel Phone 6/4-$66.42 & 6/8-$66.52, Pat O'Neal Mileage & Travel Expense 6/3-$32.94, UPS charges $4.93. July 9 - Correction: Deduct Dr. O'Neil travel from June ($-32.94) | 1790.21 | 0 | All will be distributed
Trauma Communications Center
Staffing | 308000 | N |  | N | 0 | N | N | 0 | 0 | Not moving forward with this item in FY 2010 |  | 308000 | Will not be expended
Communications Center Lead Position | 100000 | Y | Position approved by DCH thru Temp service | N | 0 | Y | N | 0 | 0 | Ryan Goodson hired - Effective 01 July 2010 salary will be from FY 2011 |  | 100000 | Will not be expended
Consultation for GTCC | 25000 | N |  | N | 0 | N | N | 0 | 0 | Not moving forward with this item in FY 2010 |  | 25000 | Will not be expended
Call recorder | 8000 | N |  | N | 0 | N | N | 0 | 0 | Not moving forward with this item in FY 2010 |  | 8000 | Will not be expended
Hardware | 100000 | N |  | N | 0 | N | N | 0 | 0 | Not moving forward with this item in FY 2010 |  | 100000 | Will not be expended
Software | 300000 | N |  | N | 0 | N | N | 0 | 0 | Not moving forward with purchase of this item in FY 2010. GTRI to issue RFP in FY 2010 and funding in FY 2011. |  | 300000 | Will not be expended
Building Lease | 12000 | N |  | N | 0 | N | N | 0 | 0 | Not moving forward with this item in FY 2010. |  | 12000 | Will not be expended
Water/Electricity | 6000 | N |  | N | 0 | N | N | 0 | 0 | Not moving forward with this item in FY 2010 |  | 6000 | Will not be expended
Backup generator | 5000 | N |  | N | 0 | N | N | 0 | 0 | Not moving forward with this item in FY 2010 |  | 5000 | Will not be expended
Workstations | 20000 | N |  | N | 0 | N | N | 0 | 0 | Not moving forward with this item in FY 2010 |  | 20000 | Will not be expended
New Projects and System Support
Web-based Trauma Registry Support | 49550 | N | Vendor unable to meet requirements | N | 0 | N | N | 0 | 0 | Not moving forward with this item in FY 2010 |  | 49550 | Will not be expended
National Foundation for Trauma Care | 1500 | Y |  | Y | 1500 | Y | Y | 1500 | 0 | Completed |  | 0 | All will be distributed
Telemedicine (GA Partnership TeleHealth) | 200000 | Y | Direct Grant Award | Y | 200000 | Y | N | 0 | 200000 | Grant award anticipated last week of April 2010. 14 June 2010, award letter sent to GPT 09 July GPT plan approved to begin invoicing. Contract expires 30 September 2011 |  | 0 | All will be distributed
National Science Foundation Center for Health Organization Transformation (CHOT) | 50000 | Y | Contract is moving through DCH legal process | Y | 50000 | Y | Y | 50000 | 0 | K# 41900-034-10100283 Moving thru DCH contracting process. Full 12-month membership for $50,000.00 14 June 2010 Contract executed and membership in effect for one year |  | 0 | All will be distributed
Pediatrics (Broselow Luten Solutions) | 200000 | Y | Contract is drafted and moving through DCH channels | Y | 200000 | Y | Y | 0 | 200000 | K# PH-101002/2-00 Moving thru DCH contracting process. 14 May Dr. Ashley has signed contract. Contract sent to Dr. Broselow 14 June 2010, Dr. Ashley signed Contract returned to DCH. 09 July: Contract executed with Broselow and invoices received in Commission office. Signature authorization in process. |  | 0 | All will be distributed
Trauma Center & Physician Allocation
New Trauma Center Startup Grants | 1000000 | N | Grant open for applications until 30 April | Y | 0 | N | N | 0 | 0 | DCH receiving applications. 14 May- evaluation committee met applications scored. Approval for spending to be made at 20 May Commission meeting. 14 June 2010: Commission approved spending money per evaluation subcommittee recommendations (20 May 2010) DCH in process of making awards 09 July: Funds returned back to state. This effort will be funded using FY2011 dollars |  | 1000000 | Returned to FY 2010 general fund on 30 June 2010
Level IV Trauma Centers | 54000 | Y |  | Y | 54000 | Y | Y | 54000 | 0 | 14 May - Not paid to date. 14 June 2010: Walton Medical Center Paid, Morgan Medical Center awaiting payment. 09 July: all Level IV centers paid |  | 0 | All will be distributed
Trauma Center Readiness Payments | 6696610 | Y |  | Y | 6696610 | Y | Y | 6696610 | 0 | 14 May - All centers paid in full except CHOA (x2) and Atlanta Medical. 14 June 2010 All Centers Paid except CHOA (x2) 09 July All centers paid. |  | 0 | All will be distributed
Performance Based Payment | 760380 | Y |  | Y | 760380 | Y | Y | 760380 | 0 | 14 May - All centers paid in full except CHOA (x2) and Atlanta Medical. 14 June 2010 All Centers Paid except CHOA (x2). 09 July All centers paid |  | 0 | All will be distributed
Uninsured Patient Care Payments | 6696610 | Y |  | Y | 6696610 | Y | Y | 6696610 | 0 | 14 May - All centers paid in full except CHOA (x2) and Atlanta Medical. 14 June 2010 All Centers Paid except CHOA (x2) 09 July All Centers paid 09 July Over payment the Grady of $653,204 returned back to state. |  | 653204 | Returned to general fund on 30 June 2010
EMS Allocation
EMS Uncompensated Care | 1000000 | N | Contract is being amended | Y | 1000000 | Y | Y |  | 1000000 | K# PH-10100190-99 (In process of being amended) 14 May - Amendment in DCH approval process. 14 June 2010: Amendment out to MCG for signatures 09 July: MCG amendment executed. Invoicing in process Program in process. |  | 0 | All will be distributed
EMS Vehicle Equipment Replacement Grants | 2125000 | Y | Grant open for applications until 16 April | Y | 0 | N | N |  | 1392241.3 | Scoring subcommittee to meet at DCH building in Atlanta on Friday, 30 April. 14 May- evaluation committee met applications scored. Approval for spending to be made at 20 May Commission meeting. 14 June 2010 Commission approved evaluation subcommittee recommendation. DCH in process of making awards. 09 July: $732,758.60 (funding for 10 vehicle awards) returned back to state. Remaining $1,392,241.30 (19 vehicle awards) to be expended. The outstanding 10 EMS vehicle awards will be funding using FY2011 dollars. |  | 732758.6 | Returned to FY 2010 general fund on 30 June 2010
First Responder Training | 338450 | Y | Contract is drafted and moving through DCH | Y | 338448.8 | Y | Y |  | 338450 | K# 419-034-10100284-99 14 May - Dr. Ashley to sign contract 20 May. 14 June 2010 Contract executed and begin 01 July 2010, GAEMS has one full year for deliverables 09 July: No update available |  | 0 | All will be distributed
Trauma-care Related Equipment | 338450 | Y | Contract is drafted and moving through DCH | Y | 338449.83 | Y | Y |  | 338450 | K# 419-034-10100284-99 14 May - Dr. Ashley to sign contract 20 May. 14 June 2010 Contract executed and begin 01 July 2010, GAEMS has one full year for deliverables. 09 July: No update available. |  | 0 | All will be distributed
Unbudgeted Funds
Less: 5% Anticipated Budget Adjustment | 1150000 | [8 empty] | Not available to Commission |  | 1150000 | Will not be distributed
Operations Reserve | 469400 | [8 empty] | Not available to Commission |  | 469400 | Will not be expended.
TOTAL BUDGET | 23000000
[5 empty] | Amount Distributed YTD |  |  | 14518605.2 |  |  |  |  | Percentage of total FY 2010 Trauma Commission budget
[6 empty] | Remaining To Be Distributed in FY 2010 |  |  | 3479981.88 | Amount of FY 2010 budget to be distributed by Trauma Commission |  | 17998587.08 | 78.25%
[10 empty] | Amount of FY 2010 to be returned back to General Fund |  | 5001412.82 | 21.75%
[10 empty] | Total |  | 22999999.9 | 100%
9 July 2010 Updates

## 14 June Report
Commission Approved Item/Project | Budget Amount | Process Complete? Y/N | Dated Comments | Encumbered? Y/N | Amount Encumbered | Contract Executed? Y/N | Invoiced? Y/N | Amount Paid YTD | Remaining Balance YTD | Dated Comments | Accrual Amount as of Report Date | Funds estimated available for reallocation (16April) | Reallocation Comments
OEMS/T Allocation at 3%
OEMS/T Allocation at 3% | 655500 | N |  | Partially |  | 3 of 5.5 | Partially | 655500 |  | 3 of the 5.5 positions have been filled. The 2.5 positions still outstanding are: Trauma Nurse, IT Specialist, Part-time EMS Medical Director. The two regional EMS directors are Chris Threlkeld and Shirley Starling. Amount paid to date unknown. Awaiting budget numbers: April 19, 2010 (per CLC) |  | 0 | No funds available. Commission voted to permit Dr. O'Neal to keep these funds to cover DPR salaries as necessary.
Administration and GTCNC Operations
Administrator & Bishop + Associates | 245950 | Y | Administrator added to B+A contract ($135,200 + $110,750) | Y | 245950 | Y | Y | 245950 | 0 | 5/14/2010-two payments made - $22,517 & $42,517 14 June 2010: All invoiced and paid.14June- final payments made - $44,736.43 & $25,066. Paid in Full |  | 0 | Anticipated all funds will be expended.
Administrative/business assistance | 50000 | Y | Carol Dixon hired thru ABACUS Temp Service start date: 09March2010. Contract end date uncertain. | unknown |  | Y | Ongoing | 6734.7 | 43265.3 | Salary Amount paid through 5/14/2010 - $5,744.05 Travel Reimbursemnt paid thru 5/14/2010 - $35.50 14June 2010: 5/18-Salary $955.15 | 10040.08 | 33225.22 | Estimated: 17 weeks (06 March through 30 June) at $957.34/week plus $500.00 travel expenses = $16,774.78 Need data from DCH Budget
Conference call account | 7200 | Y | Ongoing | Y | 7200 | NA | Ongoing | 1173.33 | 6026.67 | 5/14/2010-Payments of $415.29 & $272.68 14 June 2010-Payment of $180.60. | 1751.67 | 4275
Website design and maintenance | 15000 | N |  | N | 0 | N | N | 0 | 15000 | Not moving forward with this item in FY 2010 |  | 15000 | Will not be expended
Commission Travel/Per Diem | 10000 | N | Renee Morgan working with DCH | unknown |  | NA | NA | 0 | 10000 | Renee Morgan to update. |  | 10000 | Commission will not utilize
Monthly GTCNC meeting support | 2400 | Y | Ongoing | Y | 2400 | NA | Ongoing | 642.73 | 1757.27 | 5/14/2010-Curtis Chronister NextelPhone - $66.42, 5/14/2010-UPS Contract delivery fees - $82.16 14June 2010: Curtis Chronister NextelPhone 6/4-$66.42 & 6/8-$66.52, Pat O'Neal Mileage & Travel Expense 6/3-$32.94, UPS charges $4.93. | 1757.12 | 0 | All will be distributed
Trauma Communications Center
Staffing | 308000 | N |  | N | 0 | N | N | 0 | 308000 | Not moving forward with this item in FY 2010 |  | 308000 | Will not be expended
Communications Center Lead Position | 100000 | Y | Position approved by DCH thru Temp service | Y | 100000 | Y | N | 0 | 100000 | Temp agency is accepting resumes. |  | 100000 | Will not be expended
Consultation for GTCC | 25000 | N |  | N | 0 | N | N | 0 | 25000 | Not moving forward with this item in FY 2010 |  | 25000 | Will not be expended
Call recorder | 8000 | N |  | N | 0 | N | N | 0 | 8000 | Not moving forward with this item in FY 2010 |  | 8000 | Will not be expended
Hardware | 100000 | N |  | N | 0 | N | N | 0 | 100000 | Not moving forward with this item in FY 2010 |  | 100000 | Will not be expended
Software | 300000 | N |  | N | 0 | N | N | 0 | 300000 | Not moving forward with purchase of this item in FY 2010. GTRI to issue RFP in FY 2010 and funding in FY 2011. |  | 300000 | Will not be expended
Building Lease | 12000 | N |  | N | 0 | N | N | 0 | 12000 | Not moving forward with this item in FY 2010. |  | 12000 | Will not be expended
Water/Electricity | 6000 | N |  | N | 0 | N | N | 0 | 6000 | Not moving forward with this item in FY 2010 |  | 6000 | Will not be expended
Backup generator | 5000 | N |  | N | 0 | N | N | 0 | 5000 | Not moving forward with this item in FY 2010 |  | 5000 | Will not be expended
Workstations | 20000 | N |  | N | 0 | N | N | 0 | 20000 | Not moving forward with this item in FY 2010 |  | 20000 | Will not be expended
New Projects and System Support
Web-based Trauma Registry Support | 49550 | N | Vendor unable to meet requirements | N | 0 | N | N | 0 | 49550 | Not moving forward with this item in FY 2010 |  | 49550 | Will not be expended
National Foundation for Trauma Care | 1500 | Y |  | Y | 1500 | Y | Y | 1500 | 0 | Completed |  | 0 | All will be distributed
Telemedicine (GA Partnership TeleHealth) | 200000 | Y | Direct Grant Award | Y | 200000 | N | N | 0 | 200000 | Grant award anticipated last week of April 2010. 14 June 2010, award lettter sent to GPT |  | 0 | All will be distributed
National Science Foundation Center for Health Organization Transformation (CHOT) | 50000 | Y | Contract is moving through DCH legal process | Y | 50000 | Y | Y | 50000 | 0 | K# 41900-034-10100283 Moving thru DCH contracting process. Full 12-month membership for $50,000.00 14 June 2010 Contract executed and membership in effect for one year |  | 0 | All will be distributed
Pediatrics (Broselow Luten Solutions) | 200000 | Y | Contract is drafted and moving through DCH channels | Y | 200000 | N | N | 0 | 200000 | K# PH-101002/2-00 Moving thru DCH contracting process. 14 May Dr. Ashley has signed contract. Contract sent to Dr. Broselow 14 June 2010, Dr. Ashley signed Contract returned to DCH |  | 0 | All will be distributed
Trauma Center & Physician Allocation
New Trauma Center Startup Grants | 1000000 | N | Grant open for applications until 30 April | Y | 1000000 | N | N |  | 1000000 | DCH receiving applications. 14 May- evaluation committee met applications scored. Approval for spending to be made at 20 May Commission meeting. 14 June 2010: Commission apporved spending money per evaluation subcommittee recommendations (20 May 2010) DCH in process of making awards |  | 0 | All will be distributed
Level IV Trauma Centers | 54000 | Y |  | Y | 54000 | Y | Partially | 27000 | 27000 | 14 May - Not paid to date. 14 June 2010: Walton Medical Center Paid, Morgan Medical Center awaiting payment |  | 0 | All will be distributed
Trauma Center Readiness Payments | 6696610 | Y |  | Y | 6696610 | Y | Partially | 5841724 | 854886 | 14 May - All centers paid in full except CHOA (x2) and Atlanta Medical. 14 June 2010 All Centers Paid except CHOA (x2) |  | 0 | All will be distributed
Performance Based Payment | 760380 | Y |  | Y | 760380 | Y | Partially | 663310 | 97070 | 14 May - All centers paid in full except CHOA (x2) and Atlanta Medical. 14 June 2010 All Centers Paid except CHOA (x2) |  | 0 | All will be distributed
Uninsured Patient Care Payments | 6696610 | Y |  | Y | 6696610 | Y | Partially | 6615734 | 80876 | 14 May - All centers paid in full except CHOA (x2) and Atlanta Medical. 14 June 2010 All Centers Paid except CHOA (x2) |  | 0 | All will be distributed
EMS Allocation
EMS Uncompensated Care | 1000000 | N | Contract is being amended | Y | 1000000 |  |  |  | 1000000 | K# PH-10100190-99 (In process of being amended) 14 May - Amendment in DCH approval process. 14 June 2010: Amendment out to MCG for signatures |  | 0 | All will be distributed
EMS Vehicle Equipment Replacement Grants | 2125000 | Y | Grant open for applications until 16 April | Y | 2125000 | N | N |  | 2125000 | Scoring subcommittee to meet at DCH building in Atlanta on Friday, 30 April. 14 May- evaluation committee met applications scored. Approval for spending to be made at 20 May Commission meeting. 14 June 2010 Commission approved evaluation subcommittee recommendation. DCH in process of making awards |  | 0 | All will be distributed
First Responder Training | 338450 | Y | Contract is drafted and moving through DCH | Y | 338448.8 | Y | Y |  | 338450 | K# 419-034-10100284-99 14 May - Dr. Ashley to sign contract 20 May. 14 June 2010 Contract ececuted and begin 01 July 2010, GAEMS has one full year for deliverables |  | 0 | All will be distributed
Trauma-care Related Equipment | 338450 | Y | Contract is drafted and moving through DCH | Y | 338449.83 | Y | Y |  | 338450 | K# 419-034-10100284-99 14 May - Dr. Ashley to sign contract 20 May. 14 June 2010 Contract ececuted and begin 01 July 2010, GAEMS has one full year for deliverables |  | 0 | All will be distributed
Unbudgeted Funds
Less: 5% Anticipated Budget Adjustment | 1150000 | [7 empty] | 1150000 | Remains available to Commission |  | 1150000 | Will not be distributed
Operations Reserve | 469400 | [7 empty] | 469400 | Remains available to Commission |  | 469400 | Will not be expended.
TOTAL BUDGET | 23000000
[6 empty] | Amount Paid YTD |  | 14109268.76 |  |  |  |  | Percentage of total FY 2010 Trauma Commission budget
[10 empty] | Amount of FY 2010 budget to be distributed by Trauma Commission |  | 20384549.63 | 88.63%
[10 empty] | Amount of FY 2010 to be returned back to General Fund |  | 2615450.22 | 11.37%
[10 empty] | Total |  | 22999999.85 | 100%
14 June Updates

## 14 May Report
Commission Approved Item/Project | Budget Amount | Process Complete? Y/N | Dated Comments | Encumbered? Y/N | Amount Encumbered | Contract Executed? Y/N | Invoiced? Y/N | Amount Paid YTD | Remaining Balance YTD | Dated Comments | Accrual Amount from 16 Apr | Funds estimated available for reallocation (16April) | Reallocation Comments
OEMS/T Allocation at 3%
OEMS/T Allocation at 3% | 655500 | N |  | Partially |  | 3 of 5.5 | Partially |  | 655500 | 3 of the 5.5 positions have been filled. The 2.5 positions still outstanding are: Trauma Nurse, IT Specialist, Part-time EMS Medical Director. The two regional EMS directors are Chris Threlkeld and Shirley Starling. Amount paid to date unknown. Awaiting budget numbers: April 19, 2010 (per CLC) |  | 0 | No funds available. Commission voted to permit Dr. O'Neal to keep these funds to cover DPR salaries as necessary.
Administration and GTCNC Operations
Administrator & Bishop + Associates | 245950 | Y | Administrator added to B+A contract ($135,200 + $110,750) | Y | 245950 | Y | Ongoing | 175884 | 70066 | 5/14/2010-two payments made - $22,517 & $42,517 |  | 0 | Anticipated all funds will be expended.
Administrative/business assistance | 50000 | Y | Carol Dixon hired thru ABACUS Temp Service start date: 09March2010. Contract end date uncertain. | unknown |  | Y | Ongoing | 5779.55 | 44220.45 | Salary Amount paid through 5/14/2010 - $5,744.05 Travel Reimbursemnt paid thru 5/14/2010 - $35.50 | 16774.78 | 33225.22 | Estimated: 17 weeks (06 March through 30 June) at $957.34/week plus $500.00 travel expenses = $16,774.78 Need data from DCH Budget
Conference call account | 7200 | Y | Ongoing | Y | 7200 | NA | Ongoing | 992.73 | 6207.27 | 5/14/2010-Payments of $415.29 & $272.68 | 2925 | 4275 | Account active beginning 15 September 2009. Estimated usage is $450.00 per month for 9.5 months = $4,275.00 $7,200 - $4,275 =$2,925
Website design and maintenance | 15000 | N |  | N | 0 | N | N | 0 | 15000 | Not moving forward with this item in FY 2010 |  | 15000 | Will not be expended
Commission Travel/Per Diem | 10000 | N | Renee Morgan working with DCH | unknown |  | NA |  |  | 10000 | Renee Morgan to update. |  | 10000 | Commission will not utilize
Monthly GTCNC meeting support | 2400 | Y | Ongoing | Y | 2400 | NA | Ongoing | 471.92 | 1928.08 | 5/14/2010-Curtis Chronister NextelPhone - $66.42, 5/14/2010-UPS Contract delivery fees - $82.16 | 405.5 | 1994.5 | No further use anticipated
Trauma Communications Center
Staffing | 308000 | N |  | N | 0 | N | N | 0 | 308000 | Not moving forward with this item in FY 2010 |  | 308000 | Will not be expended
Communications Center Lead Position | 100000 | Y | Position approved by DCH thru Temp service | Y | 100000 | Y | N | 0 | 100000 | Temp agency is accepting resumes. |  | 100000 | Will not be expended
Consultation for GTCC | 25000 | N |  | N | 0 | N | N | 0 | 25000 | Not moving forward with this item in FY 2010 |  | 25000 | Will not be expended
Call recorder | 8000 | N |  | N | 0 | N | N | 0 | 8000 | Not moving forward with this item in FY 2010 |  | 8000 | Will not be expended
Hardware | 100000 | N |  | N | 0 | N | N | 0 | 100000 | Not moving forward with this item in FY 2010 |  | 100000 | Will not be expended
Software | 300000 | N |  | N | 0 | N | N | 0 | 300000 | Not moving forward with purchase of this item in FY 2010. GTRI to issue RFP in FY 2010 and funding in FY 2011. |  | 300000 | Will not be expended
Building Lease | 12000 | N |  | N | 0 | N | N | 0 | 12000 | Not moving forward with this item in FY 2010. |  | 12000 | Will not be expended
Water/Electricity | 6000 | N |  | N | 0 | N | N | 0 | 6000 | Not moving forward with this item in FY 2010 |  | 6000 | Will not be expended
Backup generator | 5000 | N |  | N | 0 | N | N | 0 | 5000 | Not moving forward with this item in FY 2010 |  | 5000 | Will not be expended
Workstations | 20000 | N |  | N | 0 | N | N | 0 | 20000 | Not moving forward with this item in FY 2010 |  | 20000 | Will not be expended
New Projects and System Support
Web-based Trauma Registry Support | 49550 | N | Vendor unable to meet requirements | N | 0 | N | N | 0 | 49550 | Not moving forward with this item in FY 2010 |  | 49550 | Will not be expended
National Foundation for Trauma Care | 1500 | Y |  | Y | 1500 | Y | Y | 1500 | 0 | Completed |  | 0 | All will be distributed
Telemedicine (GA Partnership TeleHealth) | 200000 | Y | Direct Grant Award | Y | 200000 | N | N | 0 | 200000 | Grant award anticipated last week of April |  | 0 | All will be distributed
National Science Foundation Center for Health Organization Transformation (CHOT) | 50000 | Y | Contract is moving through DCH legal process | Y | 50000 | N | N | 50000 | 0 | K# 41900-034-10100283 Moving thru DCH contracting process. Full 12-month membership for $50,000.00 | 50000 | 0 | All will be distributed
Pediatrics (Broselow Luten Solutions) | 200000 | Y | Contract is drafted and moving through DCH channels | Y | 200000 | N | N | 0 | 200000 | K# PH-101002/2-00 Moving thru DCH contracting process. 14 May Dr. Ashley has signed contract. Contract sent to Dr. Broselow |  | 0 | All will be distributed
Trauma Center & Physician Allocation
New Trauma Center Startup Grants | 1000000 | N | Grant open for applications until 30 April | Y | 1000000 | N | N |  | 1000000 | DCH receiving applications. 14 May- evaluation committee met applications scored. Approval for spending to be made at 20 May Commission meeting. |  | 0 | All will be distributed
Level IV Trauma Centers | 54000 | Y |  | Y | 54000 | Y | Partially |  | 54000 | 14 May - Not paid to date. |  | 0 | All will be distributed
Trauma Center Readiness Payments | 6696610 | Y |  | Y | 6696610 | Y | Partially | 5414281 | 1282329 | 14 May - All centers paid in full except CHOA (x2) and Atlanta Medical. |  | 0 | All will be distributed
Performance Based Payment | 760380 | Y |  | Y | 760380 | Y | Partially | 614775 | 145605 | 14 May - All centers paid in full except CHOA (x2) and Atlanta Medical. |  | 0 | All will be distributed
Uninsured Patient Care Payments | 6696610 | Y |  | Y | 6696610 | Y | Partially | 6074770 | 621840 | 14 May - All centers paid in full except CHOA (x2) and Atlanta Medical. |  | 0 | All will be distributed
EMS Allocation
EMS Uncompensated Care | 1000000 | N | Contract is being amended | Y | 1000000 |  |  |  | 1000000 | K# PH-10100190-99 (In process of being amended) 14 May - Amendment in DCH approval process. |  | 0 | All will be distributed
EMS Vehicle Equipment Replacement Grants | 2125000 | Y | Grant open for applications until 16 April | Y | 2125000 | N | N |  | 2125000 | Scoring subcommittee to meet at DCH building in Atlanta on Friday, 30 April. 14 May- evaluation committee met applications scored. Approval for spending to be made at 20 May Commission meeting. |  | 0 | All will be distributed
First Responder Training | 338450 | Y | Contract is drafted and moving through DCH | Y | 338448.8 | N | N |  | 338450 | K# 419-034-10100284-99 14 May - Dr. Ashley to sign contract 20 May. |  | 0 | All will be distributed
Trauma-care Related Equipment | 338450 | Y | Contract is drafted and moving through DCH | Y | 338449.83 | N | N |  | 338450 | K# 419-034-10100284-99 14 May - Dr. Ashley to sign contract 20 May. |  | 0 | All will be distributed
Unbudgeted Funds
Less: 5% Anticipated Budget Adjustment | 1150000 | [7 empty] | 1150000 | Remains available to Commission |  | 1150000 | Will not be distributed
Operations Reserve | 469400 | [7 empty] | 469400 | Remains available to Commission |  | 469400 | Will not be expended.
TOTAL BUDGET | 23000000
[6 empty] | Amount Paid YTD |  | 12338454.2 |  |  |  |  | Percentage of total FY 2010 Trauma Commission budget
[10 empty] | Amount of FY 2010 budget to be distributed by Trauma Commission |  | 20382555.28 | 88.62%
[10 empty] | Amount of FY 2010 to be returned back to General Fund |  | 2617444.72 | 11.38%
[10 empty] | Total |  | 23000000 | 100%
14 May Updates

## 09 April Report
Commission Approved Item/Project | Budget Amount | Process Complete? Y/N | Dated Comments | Encumbered? Y/N | Amount Encumbered | Contract Executed? Y/N | Invoiced? Y/N | Amount Paid YTD | Remaining Balance YTD | Dated Comments
OEMS/T Allocation at 3%
OEMS/T Allocation at 3% | 655500 | N |  | Partially |  | 3 of 5.5 | Partially |  | 655500 | 3 of the 5.5 positions have been filled. The 2.5 positions still outstanding are: Trauma Nurse, IT Specialist, Part-time EMS Medical Director. The two regional EMS directors are Chris Threlkeld and Shirley Starling. Amount paid to date unknown. Awaiting budget numbers: April 19, 2010 (per CLC)
Administration and GTCNC Operations
Administrator & Bishop + Associates | 245950 | Y | Administrator added to B+A contract ($135,200 + $110,750) | Y | 245950 | Y | Ongoing | 110850 | 135100 | B+A Contract in FY 2011 will be new procurement. Deliverables to be presented to Commission for approval.
Administrative/business assistance | 50000 | Y | Carol Dixon hired thru ABACUS Temp Service start date: 09March2010. Contract end date uncertain. | unknown |  | Y | Ongoing |  | 50000 | Carol receiving salary. Amount paid from budget to date unknown.
Conference call account | 7200 | Y | Ongoing | Y | 7200 | NA | Ongoing | 304.76 | 6895.24 | No documentation available.
Website design and maintenance | 15000 | N |  | N | 0 | N | N | 0 | 15000 | Not moving forward with this item in FY 2010
Commission Travel/Per Diem | 10000 | N | Renee Morgan working with DCH | unknown |  | NA |  |  | 10000 | Renee Morgan to update.
Monthly GTCNC meeting support | 2400 | Y | Ongoing | Y | 2400 | NA | Ongoing | 405.5 | 1994.5
Trauma Communications Center
Staffing | 308000 | N |  | N | 0 | N | N | 0 | 308000 | Not moving forward with this item in FY 2010
Communications Center Lead Position | 100000 | Y | Position approved by DCH thru Temp service | Y | 100000 | Y | N | 0 | 100000 | Temp agency is accepting resumes.
Consultation for GTCC | 25000 | N |  | N | 0 | N | N | 0 | 25000 | Not moving forward with this item in FY 2010
Call recorder | 8000 | N |  | N | 0 | N | N | 0 | 8000 | Not moving forward with this item in FY 2010
Hardware | 100000 | N |  | N | 0 | N | N | 0 | 100000 | Not moving forward with this item in FY 2010
Software | 300000 | N |  | N | 0 | N | N | 0 | 300000 | Not moving forward with purchase of this item in FY 2010. GTRI to issue RFP in FY 2010 and funding in FY 2011.
Building Lease | 12000 | N |  | N | 0 | N | N | 0 | 12000 | Not moving forward with this item in FY 2010.
Water/Electricity | 6000 | N |  | N | 0 | N | N | 0 | 6000 | Not moving forward with this item in FY 2010
Backup generator | 5000 | N |  | N | 0 | N | N | 0 | 5000 | Not moving forward with this item in FY 2010
Workstations | 20000 | N |  | N | 0 | N | N | 0 | 20000 | Not moving forward with this item in FY 2010
New Projects and System Support
Web-based Trauma Registry Support | 49550 | N | Vendor unable to meet requirements | N | 0 | N | N | 0 | 49550 | Not moving forward with this item in FY 2010
National Foundation for Trauma Care | 1500 | Y |  | Y | 1500 | Y | Y | 1500 | 0 | Completed
Telemedicine (GA Partnership TeleHealth) | 200000 | Y | Direct Grant Award | Y | 200000 | N | N | 0 | 200000 | Grant award anticipated last week of April
National Science Foundation Center for Health Organization Transformation (CHOT) | 50000 | Y | Contract is moving through DCH legal process | Y | 8333 | N | N | 0 | 50000 | K# 41900-034-10100283 Moving thru DCH contracting process. The $8,333.00 will be for two months and contract will have option for four renewals.
Pediatrics (Broselow Luten Solutions) | 200000 | Y | Contract is drafted and moving through DCH channels | Y | 200000 | N | N | 0 | 200000 | K# PH-101002/2-00 Moving thru DCH contracting process.
Trauma Center & Physician Allocation
New Trauma Center Startup Grants | 1000000 | N | Grant open for applications until 30 April | Y | 1000000 | N | N |  | 1000000 | DCH receiving applications
Level IV Trauma Centers | 54000 | Y |  | Y | 54000 | Y | Partially |  | 54000 | detail not available
Trauma Center Readiness Payments | 6696610 | Y |  | Y | 6696610 | Y | Partially |  | 6696610 | detail not available
Performance Based Payment | 760380 | Y |  | Y | 760380 | Y | Partially |  | 760380 | detail not available
Uninsured Patient Care Payments | 6696610 | Y |  | Y | 6696610 | Y | Partially |  | 6696610 | detail not available
EMS Allocation
EMS Uncompensated Care | 1000000 | N | Contract is being amended | Y | 1000000 |  |  |  | 1000000 | K# PH-10100190-99 (In process of being amended)
EMS Vehicle Equipment Replacement Grants | 2125000 | Y | Grant open for applications until 16 April | Y | 2125000 | N | N |  | 2125000 | Scoring subcommittee to meet at DCH building in Atlanta on Friday, 30 April.
First Responder Training | 338450 | Y | Contract is drafted and moving through DCH | Y | 338448.8 | N | N |  | 338450 | K# 419-034-10100284-99
Trauma-care Related Equipment | 338450 | Y | Contract is drafted and moving through DCH | Y | 338449.83 | N | N |  | 338450 | K# 419-034-10100284-99
Unbudgeted Funds
Less: 5% Anticipated Budget Adjustment | 1150000 | [7 empty] | 1150000 | Remains available to Commission
Operations Reserve | 469400 | [7 empty] | 469400 | Remains available to Commission
TOTAL BUDGET | 23000000 | [6 empty] | 113060.26 | 22886939.74